## Res Care
Evaluation Plan - Residential Care Initiative DRAFT - Updated May 25, 2017
System level outcomes: - Improved patient - provider experience - Reduced unnecessary or inappropriate hospital transfers - Reduced cost/patient as a result of a higher quality of care | Best practice expectations: • 24/7 availability and on-site attendance, when required • Proactive visits to residents • Meaningful medication reviews • Completed documentation • Attendance at case conferences
GOALS/OUTCOMES | OBJECTIVES | YES/NO & PRIORITY | DIFFICULTY TO MEASURE | INDICATOR | METHODS | RESPONSIBILITY FOR DATA COLLECTION | TARGET POPULATION | TIMEFRAME
1. Improved Patient-Provider Experience | 1.1 Increased number/porportion of care conferences attended by MRPs | Yes | L | 1. # of care conferences attended by PCP as a % of total care conferences booked | 1. Data from facilities as of January, 2017 | 4. Facility provides | 4. Residents & PCPs | Quarterly
| 1.2Increased facility satisfaction with MRP role addressing five best practice areas (including 24x7 coverage and on-site attendance when needed) | Yes | L | 2. Facility satisfaction reported on best practices | 2. Quarterly survey sent to facilities to complete & returned to project | 2. Provincial team sends, RCI WG provides, discusses | 2. Residents | On-going (April 1st 2016- March 31st 2017)
| 1.3.1 PCP Satisfaction with workload associated with 24x7 coverage in res care 1.3.2 # of times facility unable to get ahold of PCP when needed | Yes | M | 3.1 Facility satisfaction on quarterly report 3.2 PCP satisfaction reported 3.3 # of times facility could not get ahold of PCP | 3.1 Quarterly survey to facilities 3.2 Consider through survey - to be further discussed. 3.3 Feedback from Med Director monitoring | 3.1 - 3.3 Facilities, DOCs, Medical Directors, PCPs | 3. Residents | RCI WG meetings & Quarterly
2. Reduced Unecessary or Inappropriate Hospital Transfers | 2.1 Increased knowledge of care plan goals for resident, across multi disciplinary team (PCP, Nurse, Phamacist) | Yes - Small group to work on how to make care plan goals meaningful, consistent and accessible. See meeting minutes Apr 26 WG | H | 4. # of PCPs that say they see/know the care plan goals OR evidence of care plan goals being used in med reviews | 4. Monitor small group working on this to determine progress towards objective. | 4. PCPs and Facilities | 4. PCPs, Nurses, Pharmacists | Quarterly
3. Reduced Cost/Patient as a Result of a Higher Quality of Care | 3.1 Increased number of meaningful medication reviews being done (MRP, Pharmacist, facility together) | Yes - Already measuring through "Smiley" quarterly report & through tracking of MMRs in invoices. | M | 1. # of meaningful medication reviews done with more than provider involved OR with all three - PCP, Nurse, and Pharmacist | 1. Quarterly "Smiley face" report done by facilities 2. Tracking of medication reviews (overall numbers) through invoices submitted. | 1. Facilities, PCPs | 1. Residents | On-going Quarterly
| 3.2 Reduced number of ED visits, moving in line with number of ED visits for health authority overall | Yes- 26 WG - we will keep this measure. It is available on report from IH to facilities quarterly. | L | 3. # of ED visits for each CV facility compared to # for HA overall | 3. Need to ask Facilities for their quarterly report from IH and/or ask IH to make it available to Res Care Med Lead for Geo or to the RCI | 3. Island Health, Facilities | 3. Residents | 3. Quarterly
| 3.3 Increased satisfaction with discharge from hospital to res care admissions process (on hold pending work to be done post hospital transition) | Yes - See Apr 26 WG meeting minutes. | M | 4. Satisfaction - facilities and PCPs re: admissions | 4. To be confirmed based on working sub-group. | 4. Res Care Initiative Staff | 4. PCPs, DOCs/facilites | 4. Yearly - to be confirmed
The following potential indicators were removed from the draft plan at the Apr 26 WG meeting.
2. Reduced Unecessary or Inappropriate Hospital Transfers | 1. All patients have MOST orders in place, with clarity re: plan for hospital transfers or not. (Idea is that clarity through MOST will help to reduce some unncessary transfers) | No - See meeting minutes Apr 26 WG | M | 1. # of MOST Orders in place in each facility as a % of total residents | 1. Potentially facilities to provide update? Discuss | 1. Facilities? -Division to report monthly | 1. Patients in Res Care and going into Res Care | 1. Jan 1 - Jun 30, 2017
2. Reduced Unecessary or Inappropriate Hospital Transfers | 2. Regular proactive visits to residents | No-See meeting minutes Apr 26 WG | H | 2. # of proactive visits done per facility (how to measure - random audit of charts or through quarterly survey of facilities enough? | 2. Was supposed to come from MOH, can facilities provide or some other way? There is feedback on the report from facilities. | 2. TBD | 2. Residents | Ongoing Quarterly
| 3. Improved access between PCP progress notes and nurse notes about residents. (PCP can see nurse notes and vicea versa) | No-See meeting minutes Apr 26 WG | M | 3. # of PCPs and Facilities that say they can see each others' notes | 3. Make it part of a survey/random sample survey? | 3. TBD | 3. PCPs and Nurses | Ongoing Quarterly
3. Reduced Cost/Patient as a Result of a Higher Quality of Care | 2. Reduced number of residents on over 9 medications | No - See meeting minutes Apr 26 WG - determined too complex to measure separately & is measured through CIHI | L | 2. # of residents on 9+ medications by facility | 2. - Was supposed to come from MOH - Can get some info from Invoices submitted | 2. MOH was to provide - haven't yet. - Division (invoices) - Facilities? | 2. Residents | On-going Quarterly